## Deliverables
NEU IP - Synergetic data delivery
April 2007
This time chart will be updated as the project unfolds. Some time milestones are provisional and some datasets may be currently missing from the table.
If you are involved in a NEU activity that will deliver data (observation, synthesis or model output) which does not appear in this time chart, please contact Bill Bealey (bib@ceh.ac.uk)
with detailed instructions (Activity number, dataset type and content, collection and submission times, use within NEU) so that the table can be updated.
Red arrows signal datasets feeding the activities to which they point.
Data centres are EIP = Environmenatl Informatics Programme (CEH Lancaster) and JRC = Joint Research Centre (EC Ispra).
During the development period of the NEU relational database at EIP (i.e. until end of 2007), NEU data will temporarily be archived on the NEU website, for later transfer to EIP.
The end dates of the submission periods (shown as orange horizontal bars in the "Month" columns) are deadlines for submission to the data centres. Submission deadlines will be advertised separately on the NEU website.
It is each investigator's responsibility to ensure that their datasets are archived at the designated data centre (NEU website, EIP or JRC) by the deadlines shown.
It is the Component Data Managers' responsibility to check that submission deadlines are known and met by the data providers within their component.
In some cases to be agreed by the participants, data will be gathered by the Component Data Managers (DM) first and uploaded to the Data Centre by them.
| Component |  |  | C1 |  |  |  | C2 |  | C3 |  |  | C4 |  | C5 |  | C6 |  | Component
| Activity |  |  | A1.5 |  | A1.3 | [12 empty] | Activity
Public release date | Year | Month | Month # | Collection | Submission | Collection | Submission | Collection | Submission | Collection, model set up and runs |  | Submission | Collection | Submission | Collection | Submission | Collection | Submission | Month # | Month | Year
| 2006 | Feb | 1 |  |  |  |  | Gathering of historical data |  |  | Observational data gathering (NOFRETETE, GREENGRASS, etc.) |  |  |  | WP 5.1 |  |  |  | 1 | Feb | 2006
|  | Mar | 2 | [15 empty] | 2 | Mar
|  | Apr | 3 | [15 empty] | 3 | Apr
|  | May | 4 | [15 empty] | 4 | May
|  | Jun | 5 | [15 empty] | 5 | Jun
|  | Jul | 6 | [15 empty] | 6 | Jul
|  | Aug | 7 | Observations at L1 sites |  | Observations at the 13 L3 sites |  | Manipulation experiments | [10 empty] | 7 | Aug
|  | Sep | 8 | [15 empty] | 8 | Sep
|  | Oct | 9 | [15 empty] | 9 | Oct
|  | Nov | 10 | [15 empty] | 10 | Nov
|  | Dec | 11 | [15 empty] | 11 | Dec
| 2007 | Jan | 12 | Observations at L1 sites |  | Observations at the 13 L3 sites | [12 empty] | 12 | Jan | 2007
30 Apr 2012 |  | Feb | 13 |  | L1 site data (Aug-Dec) à NEU web |  | L3 site data (Aug-Dec) à NEU web |  |  |  |  | Observation data synthesis à NEU web |  |  |  | DB set up by WP 5.1 à JRC |  |  | 13 | Feb
|  | Mar | 14 | [15 empty] | 14 | Mar
|  | Apr | 15 | [6 empty] | Core models preliminary set up | [8 empty] | 15 | Apr
|  | May | 16 | [15 empty] | 16 | May
|  | Jun | 17 | [15 empty] | 17 | Jun
30 Sep 2012 |  | Jul | 18 | Observations at L1 sites | L1 site data (Jan-Jun) à NEU web | Observations at the 13 L3 & 8 L2 sites | L3 site data (Jan-Jun) à NEU web | Manipulation experiments | Hist. + manip. (Jul-Jun) data à C2 DM | [5 empty] | First model runs |  |  |  | 18 | Jul
|  | Aug | 19 | [6 empty] | European upscaling of detailed ecosystem models | [8 empty] | 19 | Aug
|  | Sep | 20 | [15 empty] | 20 | Sep
30 Oct 2012 |  | Oct | 21 | [5 empty] | à NEU web | [9 empty] | 21 | Oct
|  | Nov | 22 | [15 empty] | 22 | Nov
|  | Dec | 23 | [15 empty] | 23 | Dec
31 Jan 2013 | 2008 | Jan | 24 | Observations at L1 sites | L1 site data (Jul-Dec) à EIP | Observations at the 8 L2 & 13 L3 sites | L2 + L3 site data (Jul-Dec) à EIP | Manipulation experiments | Manipulation data (Jul-Dec) à EIP | [9 empty] | 24 | Jan | 2008
|  | Feb | 25 | [15 empty] | 25 | Feb
|  | Mar | 26 | [15 empty] | 26 | Mar
|  | Apr | 27 | [15 empty] | 27 | Apr
|  | May | 28 | [15 empty] | 28 | May
|  | Jun | 29 | [15 empty] | 29 | Jun
|  | Jul | 30 | Observations at L1 sites | L1 site data (Jan-Jun) à EIP | Observations at the 8 L2 & 13 L3 sites | L2 + L3 site data (Jan-Jun) à EIP | Manipulation experiments | Manipulation data (Jan-Jun) à EIP | [6 empty] | Results from first model runs à JRC |  |  | 30 | Jul
|  | Aug | 31 | [7 empty] | Application of models to C2 core manipulation sites (Months 7-30) | [7 empty] | 31 | Aug
|  | Sep | 32 | [15 empty] | 32 | Sep
|  | Oct | 33 | [15 empty] | 33 | Oct
|  | Nov | 34 | [15 empty] | 34 | Nov
|  | Dec | 35 | [15 empty] | 35 | Dec
| 2009 | Jan | 36 | Observations at L1 sites | L1 site data (Jul-Dec) à EIP | Observations at the 8 L2 & 13 L3 sites | L2 + L3 site data (Jul-Dec) à EIP | Manipulation experiments | Manipulation data (Jul-Dec) à EIP | [9 empty] | 36 | Jan | 2009
|  | Feb | 37 | [8 empty] | Model results à JRC | [6 empty] | 37 | Feb
|  | Mar | 38 | [15 empty] | 38 | Mar
|  | Apr | 39 | [7 empty] | European upscaling of high temporal resolution ecosystem model results. Comparison with multi-sector model results. | Core manip. site simulations à EIP | [6 empty] | 39 | Apr
|  | May | 40 | [15 empty] | 40 | May
|  | Jun | 41 | [15 empty] | 41 | Jun
|  | Jul | 42 | Observations at L1 sites | L1 site data (Jan-Jun) à EIP | Observations at the 8 L2 & 13 L3 sites | L2 + L3 site data (Jan-Jun) à EIP | Manipulation experiments | Manipulation data (Jan-Jun) à EIP | [9 empty] | 42 | Jul
|  | Aug | 43 | [15 empty] | 43 | Aug
|  | Sep | 44 | [15 empty] | 44 | Sep
|  | Oct | 45 | [15 empty] | 45 | Oct
|  | Nov | 46 | [15 empty] | 46 | Nov
|  | Dec | 47 | [15 empty] | 47 | Dec
| 2010 | Jan | 48 | Observations at L1 sites | L1 site data (Jul-Dec) à EIP | Observations at the 8 L2 & 13 L3 sites | L2 + L3 site data (Jul-Dec) à EIP | Manipulation experiments | Manipulation data (Jul-Dec) à EIP | Core site simulations including manipulation experiments (Months 7-54) | [8 empty] | 48 | Jan | 2010
|  | Feb | 49 | [8 empty] | Model results à JRC | [6 empty] | 49 | Feb
|  | Mar | 50 | [15 empty] | 50 | Mar
|  | Apr | 51 | [15 empty] | 51 | Apr
|  | May | 52 | [15 empty] | 52 | May
|  | Jun | 53 | [15 empty] | 53 | Jun
|  | Jul | 54 | Observations at L1 sites | L1 site data (Jan-Jun) à EIP | Observations at the 8 L2 & 13 L3 sites | L2 + L3 site data (Jan-Jun) à EIP | Manipulation experiments | Manipulation data (Jan-Jun) à EIP | [9 empty] | 54 | Jul
|  | Aug | 55 | [15 empty] | 55 | Aug
|  | Sep | 56 | [15 empty] | 56 | Sep
|  | Oct | 57 | [15 empty] | 57 | Oct
|  | Nov | 58 | [7 empty] | GHG emission scenarios | Simulation results à EIP | [6 empty] | 58 | Nov
|  | Dec | 59 | [15 empty] | 59 | Dec
| 2011 | Jan | 60 | [15 empty] | 60 | Jan | 2011
|  | Feb | 61 | – End – | L1 site data (Jul-Jan) à EIP | – End – | L2 + L3 site data (Jul-Jan) à EIP | – End – | Manipulation data (Jul-Jan) à EIP | – End – | – End – | Scenario results à EIP | – End – |  | – End – |  | – End – |  | 61 | Feb
|  | Mar | 62 | [15 empty] | 62 | Mar
|  | Apr | 63 | [15 empty] | 63 | Apr
|  |  |  | A1.5 |  | A1.3
|  |  |  | C1 |  |  |  | C2 |  | C3 |  |  | C4 |  | C5 |  | C6